Is the Monitor Where the People Are? Auditing India's Air-Quality Sensor Network

Problem Statement:

Build a machine learning system that estimates population-weighted PM2.5 exposure across an Indian city using satellite data, compares it against what the city's official air-quality monitors report, and recommends where an additional monitor would most reduce that gap.

Description:

Under India's National Clean Air Programme, cities receive funding based on measured pollution reduction at their official monitoring stations — which means where a city places its monitors can quietly influence its funding, independent of real air quality. This project reconstructs population-weighted “true” exposure using satellite-derived PM2.5 and gridded population data, compares it against readings from the city's actual monitoring network, and quantifies the gap between the two. Students then apply a simple placement algorithm to recommend where the next monitor should go to best close that gap.

Dataset:

The following datasets will be provided as a ready-to-use extract as part of the project package. Original public sources are listed below for reference and attribution:

- CPCB CAAQMS Station List – locations of India's official air-quality monitoring stations; open access, XLSX (airquality.cpcb.gov.in)

- SatPM V6 Satellite-Derived PM2.5 – monthly surface PM2.5 estimates for India, 0.01°/0.1° resolution; open access, CC BY 4.0 (satpm.org)

- WorldPop India Population Counts (100m) – gridded population data; open access, CC BY 4.0 (data.humdata.org)

- OpenAQ Historical Archive – ground-monitor measurements used for validation; open access (openaq.org)

Week-by-Week Plan (8 Weeks):

- Week 1: Select 3–4 NCAP cities; load the provided CPCB station list, SatPM PM2.5 subset and WorldPop grid; explore formats and coordinate systems

- Week 2: Preprocess and align the satellite PM2.5 grid with the population grid; engineer population-weighted exposure features per city

- Week 3: Build Model 1 – a bias-correction regression calibrating satellite PM2.5 against OpenAQ ground readings

- Week 4: Build Model 2 – an alternate calibration approach (e.g. gradient boosting) and compare against Model 1

- Week 5: Evaluate both calibration models (cross-validation, error metrics); select the better-performing approach

- Week 6: Tune the selected model; apply it to compute the population-weighted exposure gap per city; implement a greedy sensor-placement algorithm recommending next monitor locations

- Week 7: Build a FastAPI endpoint serving the exposure gap and recommended placement for a queried city or ward

- Week 8: Build a dashboard with city maps showing exposure versus monitor coverage; finalize code and report

Submission Requirements:

- Cleaned satellite PM2.5, population and station datasets for chosen cities, with documentation

- Bias-correction model (satellite-to-ground) with validation metrics

- Population-weighted exposure gap analysis per city

- Sensor-placement recommendation algorithm and output

- FastAPI endpoint for exposure and placement queries

- City-level maps/dashboard and final report with policy recommendations